## Forward plan
Last updated 12/12/2022
Key Descriptions | Key Colour Code | Northern Ireland Planning Statistics Forward Work Programme (October 2020 - March 2023)
Planned Work
Planned Completion
Work underway
Complete
Work on hold
Forward Work Plan | Lead | Actions required to progress work programme | Updates / Links to relevant information / development
|  | Forward Work plan |  | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01
Publication of Quarterly & Annual Planning Official Statistics | DP Statistician | Continuing as per usual intervals, on a quarterly basis. Publication normally during March, June, September and December each year.
Production of Monthly MIS reports on Legislative Indicators - Department & Councils | DP Statistician | Ongoing in support of each quarterly publication
Production of validated quarterly OS datasets - Department & Councils | DP Statistician | Ongoing in support of each quarterly publication | bar: 2020-12-01; 2021-03-01; 2021-06-01; 2021-09-01; 2021-12-01; 2022-03-01; 2022-06-01; 2022-09-01; 2022-12-01
Annual Publication of Planning Applications Open Dataset | DP Statistician | Publishing annually following the publication of the NI Annual Planning Statistics. Available information can be found at this link: | bar: 2021-08-01; 2022-07-01
Provision of Northern Ireland Planning Statistics to the Northern Ireland Neighbourhood Information System (NINIS): a) Quarterly renewable data, b) annual suite of outputs following publication of finalised annual NI Planning Statistics | DP Statistician | Provision of data outputs to the NINIS team for publication. Current outputs can be found here: (1) annual data: https://www.ninis2.nisra.gov.uk/public/PivotGrid.aspx?ds=10075&lh=73&yn=2002-2019&sk=10&sn=People%20and%20Places&yearfilter= (2) quarterly data (a) single wind turbines https://www.ninis2.nisra.gov.uk/InteractiveMaps/People%20and%20Places/Planning/Single%20Wind%20Turbine/atlas.html, (b) solar farms https://www.ninis2.nisra.gov.uk/InteractiveMaps/People%20and%20Places/Planning/Solar%20Farm/atlas.html, (c) wind farms https://www.ninis2.nisra.gov.uk/InteractiveMaps/People%20and%20Places/Planning/Wind%20Farm/atlas.html | Current planning outputs already provided and available on NINIS | bar: 2020-12-01; 2021-03-01; 2021-07-01; 2021-09-01; 2021-12-01; 2022-03-01; 2022-07-01; 2022-09-01; 2022-12-01
Meetings of Planning Statistics Key Users Group | Principal Statistician | Next meeting planned for early 2023. | bar: 2020-11-01; 2021-03-01; 2021-12-01; 2022-02-01
Input to the development of a new planning IT system(s) to ensure analytical output and other ASRB requirements | DP Statistician | ASRB have input detailed information to clarify requirements for statistical reporting through any future system. There are regular meetings with the supplier and updates on progress relevant in this area will be communicated through user | The new Mid Ulster system went live on 22 June 2022; extracts have been developed to enable Planning Statistics to be produced for the council. The NI Planning Portal went live on 5 December 2022; work is underway to develop extracts to enable future reporting for the ten planning authorities and Department. Updates can be found in most recent planning statistics report.
Investigation into the linkage of planning approvals data to housing completions data | DP Statistician | Investigations to continue through cross-government working group | Scoping paper published | 2020-12-01: Cross Govt Planning Working Group Meeting; 2021-03-01: Cross Govt Planning Working Group Meeting; 2021-06-01: Cross Govt Planning Working Group Meeting; 2021-09-01: Cross Govt Planning Working Group Meeting; 2021-12-01: Cross Govt Planning Working Group Meeting; 2022-02-01: Cross Govt Planning Working Group Meeting; 2022-05-01: Cross Govt Planning Working Group Meeting; 2022-09-01: Cross Govt Planning Working Group Meeting
Statistical Input to development of new NI Planning Portal and testing of data prior to and throughout transfer | DP Statistician | Attend meetings/ workshops as required and provide relevant input. Carry out appropriate testing when needed.
Continued development and exploration of interactive Planning data visualisations | DP Statistician | Develop and publish new interactive planning statistics content. | Due to resource constraints unable to progress at present. | 2020-10-01: Development phase; 2020-11-01: Development phase; 2020-12-01: Development phase; 2021-01-01: Development phase; 2021-02-01: Development phase; 2021-03-01: Development phase; 2021-04-01: Development phase; 2021-05-01: Development phase; 2021-06-01: Development phase; 2021-07-01: Development phase; 2021-08-01: work on hold
Attendance at NIHE House Condition Survey steering group | Principal Statistician | HoB attended most recent steering group meeting during January 2021. Due to Covid-19, the NIHCS 2021 has been postponed until 2022. In the interim, the Housing Executive will consult with users to identify the key statistics needed, and will produce modelled statistics using data from the 2016 NIHCS. | NIHE House-Condition-Survey | bar: 2020-10-01; 2021-01-01
Attendance at Cross-Government Housing Statistics working group | DP Statistician | Head of Section to attend meetings as required. Meetings held quarterly. |  | 2021-03-01: Cross Govt Working Group Meeting; 2021-06-01: Cross Govt Working Group Meeting; 2021-09-01: Cross Govt Working Group Meeting; 2021-11-01: Cross Govt Working Group Meeting; 2022-02-01: Cross Govt Working Group Meeting; 2022-05-01: Cross Govt Working Group Meeting; 2022-09-01: Cross Govt Working Group Meeting
Review of Quality Assurance of Administrative Data Sources (QAAD) | DP Statistician | Current version | bar: 2020-10-01; 2021-05-01; 2021-12-01
Review of Background Quality Report (BQR) | DP Statistician | Current version | bar: 2020-10-01; 2021-05-01; 2021-12-01; 2022-12-01
Exploration of Reproducible Analytical Pipelines (RAP) processes | Principal Statistician | Head of Branch engaged with Office for Statistical Regulation (OSR) review of RAP processes during October 2020. ASRB Staff have all attended Intro to R training to commence skilling to allow future development of RAP processes, as resource allows. | Planning section now returned to full staffing complement. Training of new staff in 'R' is required and following that this work area will progress. | bar: 2020-10-01; 2023-02-01 to 2023-03-01
Routine update of published Ad hoc Planning Queries | DP Statistician | Quarterly update of published Ad hoc Planning Queries. | bar: 2020-10-01; 2021-01-01; 2021-04-01; 2021-07-01
Carry out Planning Statistics User Survey | DP Statistician | Carry out biennial customer survey. | The GSS are looking for feedback to help ensure that our planning statistics are valuable in informing policy and important questions for the public. You can complete the user survey here which is open until 12 January 2023. | bar: 2022-11-01 to 2023-03-01
Re-develop planning statsitics content held on NNIS to enabale it to be placed on the new NISRA Data Portal | DP Statistician | NINIS will reach end of use in June 2023. All content on NISIS is to transfer to the new NISRA Data Portal. The planning staisitcs content on NINIS needs to be reshaped for the new Data Portal. ASRB staff alongside NISRA NINIS support staff will take forward this reshaping work in early 2023. | ASRB and NINIS staff met in November 2022 to agree forward steps to progress the work. | bar: 2022-11-01 to 2023-03-01

## Planning Assessment Reqs.
Northern Ireland Planning Statistics - assessment requirements
The action plan for meeting the requirements set out in the recent Office for Statistics Regulation (the regulatory arm of the UK Statistics Authority) Assessment of Northern Ireland Planning Statistics. Details of each requirement, along with the evidence needed and the actions we intend to carry out are included below, as well as the proposed timetable for meeting each requirement.
ASSESSMENT FINDING: | REQUIREMENT: |  | EVIDENCE NEEDED: | ACTIONS REQUIRED TO GENERATE EVIDENCE: | ASRB LEAD:
VALUE
DfI should enhance the impact and insight of the planning statistics for a wider range of users and facilitate their further reuse. DfI should do this by: | 1 | a) exploring the use of maps and new forms of interactive presentation; | • Evidence that exploratory work has been carried out seeking options and viability for use of maps and interactive presentation of planning statistics. Document all exploratory work, or, • Detailed plan to introduce new interactive content, and/or • New interactive content | • Explore the example using Power BI from the Ministry of Housing, Communities & Local Government. Gather information on what software is required to develop and publish data in this format. • Check internal software availability. • Staff to receive relevant training on new software. • Ensure interactive content can be placed on Departmental website. • Develop interactive content. • Publish new content | DP Statistician
| 1 | b) improving the accessibility of underlying data from the bulletin; | • Evidence that statisticians have sought to introduce direct links to excel tables within statistical publication, or, • Introduction of direct links to specific excel tables within publication. | • Explore feasibility of having direct links to excel tables in publication rather than to a landing page. • Update process documentation with new process. • Introduce new links to Q1 2020/21 publication. | DP Statistician
| 1 | c) publishing the full range of available outputs, including the statistics key messages video and ad hoc analyses produced in response to users’ requests. | • Evidence that statisticians have sought to publish Planning Statistics key message video on Departmental website. • Publication of Planning Statistics key message video. • Publications of ad-hoc analyses produced in response to user requests on Departmental website. | • Explore feasibility of publishing Planning Statistics key message video on Departmental website and publish if feasible. • Create new webpage for publication of ad-hoc requests and upload requests periodically. | DP Statistician
DfI should set out its plans for the future development of the planning statistics in light of forthcoming changes to the planning portal, for example through a published work plan. It should also publish summary information from its key user meetings so that other users are kept informed and have opportunities to comment on proposals. | 2 | a) published work plan detailing future development of planning statistics | • Publication of Planning Statistics work plan. | • Develop a work plan for Planning Statistics and detail future developments such as new planning portal. • Web development to host new content | DP Statistician
| 2 | b) publish summary information from key user group and welcome feedback from other users. | • Publication of summary information from key user group meetings | • Summarise minutes from previous key user group meetings and publish. • Web development to host new content | DP Statistician
To enhance the public value of the NI planning activity statistics, DfI should investigate the feasibility of linking planning approvals to house building completions data. DfI should collaborate with other UK and NI statisticians as necessary to help answer key questions and enable a better understanding of the NI planning statistics in relation to the overall UK planning picture, and publish its findings. | 3 | a) investigate the feasibility of linking planning approvals and house building completions data | • Production of scoping paper | • Establish appropriate contact points within central and local government, including DfC and LPS. • Explore accessibility, timeliness and quality of required data and establish if there would be any access issues and if data access agreements would be needed. • Scope out if there has been any previous work carried out to link building control completions with planning approvals. | Grade 7 and DP Statistician
| 3 | b) collaborate with other UK and NI statisticians where necessary to answer key questions and provide clarity in relation to NI planning statistics within the UK planning picture. Publish any findings. | • Detail of any collaboration and additions made to publication • Maintain presence on relevant working groups | • Links to other jurisdictions within publication, taking views of other NS to guide suitable depth of content | DP Statistician
QUALITY
To demonstrate its continuous commitment to assured official statistics DfI should enhance the level of assurance that it seeks around planning data quality ahead of the transition to new planning portal. It should publish for users, details of its level of assurance, any potential impacts on data quality or methods, and how these impacts will be mitigated. | 4 | a) enhance the level of assurance that it seeks around planning data quality ahead of transition to new planning portal. It should publish for users, details of its level of assurance, any potential impacts on data quality or methods, and how these impacts will be mitigated. | • Publish updated QAAD, taking into account progress of new Portal development and adjust risk accordingly. • Publish updated BQR annually. • Introduction of updated user guidance quality information moving forward. | • Review quality documentation and update annually: • QAAD • BQR • User guidance in publication and published excel tables | DP Statistician

## Assessment Actions
Last updated 15/02/2020 |  |  |  |  | Northern Ireland Planning Statistics: National Statistics Assessment Action Plan
| Key Descriptions | Key Colour Code
Not Started
| Planned Work |  |  |  | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
Planned Completion
Work underway | time axis 2020-04-27 to 2020-11-13
Complete
| Requirement | Lead | Actions required to generate evidence | Updates / Links to relevant information / development | 2020-04-27: 2020-04-01; 2020-05-04: 2020-05-01; 2020-06-01: 2020-06-01; 2020-07-01: 2020-07-01; 2020-08-03: 2020-08-01; 2020-09-01: 2020-09-01; 2020-10-01: 2020-10-01; 2020-11-02: 2020-11-01
[5 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 |  |  |  |  | Week 27 |  |  |  |  | Week 28 |  |  |  |  | Week 29
|  | OSR | Assessment Report Published | bar: 2020-05-07
Assessment Report Requirements
Requirement 1: DfI should enhance the impact and insight of the planning statistics for a wider range of users and facilitate their further reuse. Examples of ways that DfI could do this are: | 1(a) exploring the use of maps and new forms of interactive presentation | DP Statistician | • Explore the example using Power BI from the Ministry of Housing, Communities & Local Government. Gather information on what software is required to develop and publish data in this format. | Planning data is available on the NI Neighbourhood Information Service and this data is provided regularly to the NINIS team, with quarterly data provided following the release of each publication for renewable content. | bar: 2020-04-27 to 2020-05-01
NINIS Annually published content provided after the publication of annual reports for the full suite of published planning applications and enforcement data. | bar: 2020-04-27 to 2020-05-01
|  | DP Statistician | • Check internal software availability | bar: 2020-04-27 to 2020-05-01
|  | DP Statistician | • Staff to receive relevant training on new software. | bar: 2020-04-27 to 2020-09-02
|  | DP Statistician | • Ensure interactive content can be placed on Departmental website. | bar: 2020-04-27
|  | DP Statistician | • Develop interactive content | The Planning Statistics data visualisation is available on the Planning Statistics landing page under the ‘Data Visualisation’ heading. Power BI content developed - unable to currently publish but exploring ways to address this and publish as soon as possible.
|  | DP Statistician | • Publish new content
| 1(b) improving the accessibility of underlying data from the bulletin. | DP Statistician | • Explore feasibility of having direct links to excel tables in publication rather than to a landing page | Links within publications now point to the relevant quarterly publication landing page, rather than the generic Planning Statistics landing page. Direct links to Excel tables would not meet current accessibility legislation. See first bulletin with these changes implemented (Q1 2020/21). These links will be used as the way forward for future bulletins. We have also updated our internal process documentation to reflect these changes. | bar: 2020-04-27
|  | DP Statistician | • Update process documentation with new process. | bar: 2020-04-27 to 2020-09-30
|  | DP Statistician | • Introduce new links to Q1 2020/21 publication. | bar: 2020-04-27 to 2020-09-18
| 1(c) publishing the full range of available outputs, including the statistics key messages video and ad hoc analyses produced in response to users’ requests. | DP Statistician | • Explore feasibility of publishing Planning Statistics key message video on Departmental website and publish if feasible. | Planning statistics key message video is now available on DfI website under the ‘Data Visualisation’ heading. | bar: 2020-04-27 to 2020-07-31
|  | DP Statistician | • Create new webpage for publication of ad-hoc requests and upload requests periodically. | Ad hoc requests now have a webpage and are updated regularly with new requests | bar: 2020-04-27 to 2020-04-29
Requirement 2: DfI should set out its plans for the future development of the planning statistics in light of forthcoming changes to the planning portal, for example through a published work plan. It should also publish summary information from its key user meetings so that other users are kept informed and have opportunities to comment on proposals. | 2(a) published work plan detailing future development of planning statistics | DP Statistician | • Develop a work plan for Planning Statistics and detail future developments such as new planning portal. | ASRB published an action plan to advise users of our progress towards the requirements of the assessment, which has now been superceded by this forward work plan. This illustrates likely developments and timescales up to end of 2022/23. This will be updated as new developments related to the NI Planning Statistics emerge. | bar: 2020-04-27 to 2020-07-31
|  | DP Statistician | • Web development to host new content | New content has been created and is now being published on the DfI website on a quarterly basis. The Planning Statistics data visualisation is available on the Planning Statistics landing page under the ‘Data Visualisation’ heading | bar: 2020-04-27 to 2020-07-31
The new NI Planning Portal section has been expanded in the publication as far as currently possible, this will be reviewed ahead of each publication and updated to reflect the most up to date position. | bar: 2020-04-27 to 2020-07-31
| 2(b) publish summary information from key user group and welcome feedback from other users. | DP Statistician | • Summarise minutes from previous key user group meetings and publish | Key user group minutes are now published on DfI website. | bar: 2020-04-27 to 2020-07-31
|  | DP Statistician | • Web development to host new content | bar: 2020-04-27 to 2020-07-31
Requirement 3: To enhance the public value of the NI planning statistics, DfI should investigate the feasibility of linking planning approvals to house building completions data, perhaps exploring this in partnership with Admin Data Research Northern Ireland. DfI should collaborate with other UK and NI statisticians as necessary to help answer key questions and enable a better understanding of the NI planning statistics in relation to the overall UK planning picture, and publish its findings. | 3(a) investigate the feasibility of linking planning approvals and house building completions data | DP Statistician | • Establish appropriate contact points within central and local government, including DfC and LPS. | Scoping paper published. | bar: 2020-04-27 to 2020-07-31
|  | DP Statistician | • Explore accessibility, timeliness and quality of required data and establish if there would be any access issues and if data access agreements would be needed. | bar: 2020-04-27 to 2020-09-29
|  | DP Statistician | • Scope out if there has been any previous work carried out to link building control completions with planning approvals. | bar: 2020-04-27 to 2020-09-29
| 3(b) collaborate with other UK and NI statisticians where necessary to answer key questions and provide clarity in relation to NI planning statistics within the UK planning picture. Publish any findings. | DP Statistician | • Links to other jurisdictions within publication, taking views of other national statistics publications to guide suitable depth of content. | Section detailing other jurisdictions has been expanded to reflect that in the England Planning Statistics publication, which is currently designated as NS (see page 28) | bar: 2020-04-27 to 2020-09-24
DfI statisticians are part of a cross-government working group, working to improve the trustworthiness, quality and value of housing and planning statistics across the UK, which most recently met on the 17 September 2020. | bar: 2020-04-27 to 2020-09-24
ASRB staff are also on the NI Housing Executive’s (NIHE) House Condition Survey working group. ASRB staff also attend the Strategic Planners Group at various key points, most recently in 2019. | bar: 2020-04-27 to 2020-09-24
Requirement 4: To demonstrate its continuous commitment to assured official statistics DfI should enhance the level of assurance that it seeks around planning data quality ahead of the transition to new planning portal. It should publish for users, details of its level of assurance, any potential impacts on data quality or methods, and how these impacts will be mitigated. | 4. enhance the level of assurance that it seeks around planning data quality ahead of transition to new planning portal. It should publish for users, details of its level of assurance, any potential impacts on data quality or methods, and how these impacts will be mitigated. | DP Statistician | • Review quality documentation and update annually: QAAD | Updated QAAD | bar: 2020-04-27 to 2020-09-24
|  | DP Statistician | • Review quality documentation and update annually: BQR | Updated BQR | bar: 2020-04-27 to 2020-09-24
|  | DP Statistician | • Review and update user guidance in publication and published excel tables. | All quality information is updated to reflect current position. User guidance in the most recent publication and tables has also been updated, including a short note on latest Portal development. ASRB has also been in contact with Planning Portal development team and chosen supplier to ensure ASRB are best placed to manage that risk in respect to planning statistics. | bar: 2020-04-27 to 2020-07-02